## Schedule
VCU School of Business and Engineering (Richmond, VA) — CM: Gilbane Building Company · 245,000 SF · 4층 · 철골+RC · $65M
원본: Penn State AE Senior Thesis 공개 포트폴리오 공정표(PDF) — 표 그대로 옮김, 선행·요약행 구조 포함
ID | Task Name | Duration | Start | Finish | Predecessors
1 | Notice to Proceed | 0 days | 2006-01-16 | 2006-01-16
2 | Start | 0 days | 2006-01-16 | 2006-01-16
3 | Sitework | 164 days | 2006-01-16 | 2006-08-31
4 | Excavate SOB for Foundations - Section A | 29 days | 2006-01-16 | 2006-02-23
5 | Excavate SOB for Foundations - Section B | 27 days | 2006-02-27 | 2006-04-04
6 | Excavate SOB for Foundations - Crescent | 18 days | 2006-03-22 | 2006-04-14
7 | Excavate SOE for Foundations - Section C | 32 days | 2006-04-05 | 2006-05-18
8 | Install Underslab Utilities - Section C | 10 days | 2006-04-28 | 2006-05-11
9 | Install Underslab Utilities - Section A | 10 days | 2006-07-06 | 2006-07-19
10 | Install Underslab Utilities - Section B | 10 days | 2006-07-26 | 2006-08-08
11 | Install Underslab Utilities - Section C | 10 days | 2006-08-10 | 2006-08-23
12 | Install Underslab Utilities - Crescent | 10 days | 2006-08-18 | 2006-08-31
13 | Cast In Place Concrete | 200 days | 2006-02-09 | 2006-11-15
14 | Place Concrete Foundations - Section A | 20 days | 2006-02-09 | 2006-03-08
15 | Place Concrete Foundations - Section B | 21 days | 2006-03-22 | 2006-04-19
16 | Place Concrete Walls - Section B | 21 days | 2006-03-22 | 2006-04-19
17 | Place Concrete Foundations - Crescent | 7 days | 2006-04-04 | 2006-04-12
18 | Place Concrete Foundations - Section C | 10 days | 2006-04-14 | 2006-04-27
19 | Place Concrete Walls - Section C | 10 days | 2006-04-14 | 2006-04-27
20 | Place Concrete Foundations - Section C | 8 days | 2006-05-08 | 2006-05-17
21 | Place Concrete Slab on Grade - Section C | 7 days | 2006-05-12 | 2006-05-22
22 | Place Concrete 1st Floor Slab - Section C | 1 day | 2006-05-22 | 2006-05-22
23 | Place Concrete Walls - Section A | 20 days | 2006-07-06 | 2006-08-02
24 | Place Concrete 2nd Floor Slab - Section C | 1 day | 2006-07-12 | 2006-07-12
25 | Place Concrete 3rd Floor Slab - Section C | 1 day | 2006-07-24 | 2006-07-24
26 | Place Concrete Slab on Grade - Section A | 10 days | 2006-07-26 | 2006-08-08
27 | Place Concrete 4th Floor Slab - Section C | 1 day | 2006-08-03 | 2006-08-03
28 | Place Concrete Roof Slab - Section C | 1 day | 2006-08-15 | 2006-08-15
29 | Roof Available - Section C | 0 days | 2006-08-23 | 2006-08-23
30 | Place Concrete Walls - Section C | 12 days | 2006-08-10 | 2006-08-25
31 | Place Concrete Walls - Crescent | 11 days | 2006-08-18 | 2006-09-01
32 | Place Concrete Slab on Grade - Crescent | 10 days | 2006-09-05 | 2006-09-18
33 | Place Concrete Slab on Grade - Section B | 8 days | 2006-09-20 | 2006-09-29
34 | Place Concrete Slab on Grade - Section C | 21 days | 2006-10-18 | 2006-11-15
35 | Water Proofing | 163 days | 2006-04-14 | 2006-11-28
36 | Waterproof Concrete - Section B | 5 days | 2006-04-14 | 2006-04-20
37 | Waterproof Concrete - Section C | 5 days | 2006-05-01 | 2006-05-05
38 | Waterproof Concrete - Section C | 5 days | 2006-08-28 | 2006-09-01
39 | Waterproof Concrete - Crescent | 6 days | 2006-08-29 | 2006-09-05
40 | Waterproof Concrete - Section A | 6 days | 2006-11-21 | 2006-11-28
41 | Structural Steel | 81 days | 2006-05-01 | 2006-08-21
42 | Install Structural Steel - Octagon | 15 days | 2006-05-01 | 2006-05-19
43 | Install Structural Steel - Section A | 15 days | 2006-05-22 | 2006-06-09
44 | Install Structural Steel - Section B | 20 days | 2006-06-21 | 2006-07-18
45 | Install Structural Steel - Crescent | 24 days | 2006-07-19 | 2006-08-21
46 | Install Structural Steel - Section C | 14 days | 2006-07-25 | 2006-08-11
47 | Roof Installation | 61 days | 2006-07-26 | 2006-10-18
48 | Install Roof - Section B | 5 days | 2006-07-26 | 2006-08-01
49 | Install Roof - Section C | 20 days | 2006-08-21 | 2006-09-15
50 | Install Roof - Crescent | 11 days | 2006-08-28 | 2006-09-11
51 | Section A Dry | 0 days | 2006-09-29 | 2006-09-29
52 | Install Roof - Section A | 13 days | 2006-10-02 | 2006-10-18
53 | SOB DRY - WEST | 0 days | 2006-11-22 | 2006-11-22
55 | SOB DRY - CRESCENT | 0 days | 2006-11-28 | 2006-11-28
57 | Fireproof Structural Steel | 41 days | 2006-07-31 | 2006-09-25
58 | Fireproof Structural Steel -Section A | 25 days | 2006-07-31 | 2006-09-01
59 | Fireproof Structural Steel - Section B | 37 days | 2006-08-04 | 2006-09-25
60 | Fireproof Structural Steel - Crescent | 26 days | 2006-08-21 | 2006-09-25
61 | Fireproof Structural Steel - Section C | 26 days | 2006-08-21 | 2006-09-25
62 | Fire Protection | 46 days | 2006-07-26 | 2006-09-27
63 | Install Fire Protection - Section C | 46 days | 2006-07-26 | 2006-09-27
64 | Install Fire Protection - Section A | 29 days | 2006-08-14 | 2006-09-21
65 | Install Fire Protection - Crescent | 20 days | 2006-08-31 | 2006-09-27
66 | Install Fire Protection - Section B | 23 days | 2006-08-28 | 2006-09-27
67 | Masonry/Precast | 181 days | 2006-08-07 | 2007-04-16
68 | Install Exterior Sheathing - Section A | 31 days | 2006-08-07 | 2006-09-18
69 | Brick and Arriscraft Veneer - Section A | 56 days | 2006-08-21 | 2006-11-06
70 | Install Exterior Sheathing - Section B | 7 days | 2006-09-19 | 2006-09-27
71 | Install Exterior Sheathing - Section C | 16 days | 2006-09-28 | 2006-10-19
72 | Install Exterior Sheathing - Octagon | 7 days | 2006-10-27 | 2006-11-06
73 | Install Exterior Sheathing - Section C | 8 days | 2006-11-07 | 2006-11-16
74 | Brick and Arriscraft Veneer - Section B | 17 days | 2006-11-07 | 2006-11-29
75 | Install Exterior Sheathing - Section B | 5 days | 2006-11-16 | 2006-11-22
76 | Install Exterior Sheathing - Crescent | 8 days | 2006-11-17 | 2006-11-28
77 | Brick and Arriscraft Veneer - Section C | 40 days | 2006-11-30 | 2007-01-24
78 | Brick and Arriscraft Veneer - Octagon | 38 days | 2007-01-25 | 2007-03-19
79 | Brick and Arriscraft Veneer - Crescent | 20 days | 2007-03-20 | 2007-04-16
81 | Windows and Glazing | 184 days | 2006-10-17 | 2007-06-29
82 | Install Windows & Glazing - Section A | 11 days | 2006-10-17 | 2006-10-31
83 | Install Windows & Glazing - Section A | 13 days | 2006-11-10 | 2006-11-28
84 | Install Windows & Glazing - Section B | 12 days | 2006-12-05 | 2006-12-20
85 | Install Windows & Glazing - Section C | 20 days | 2006-12-29 | 2007-01-25
86 | Install Windows & Glazing - Section C | 20 days | 2007-02-01 | 2007-02-28
87 | Install Windows & Glazing - Octagon | 17 days | 2007-03-01 | 2007-03-23
88 | Install Windows & Glazing - Section C | 16 days | 2007-03-26 | 2007-04-16
89 | Install Windows & Glazing - Crescent | 50 days | 2007-04-23 | 2007-06-29
90 | Install Windows & Glazing - Section B | 15 days | 2007-06-11 | 2007-06-29
91 | Wall Inspections | 122 days | 2006-09-12 | 2007-02-28
92 | Section A - Floor 1 | 2 days | 2006-09-12 | 2006-09-13
93 | Section A - Floor 2 | 2 days | 2006-09-26 | 2006-09-27
94 | Section A - Floor 3 | 2 days | 2006-10-11 | 2006-10-12
95 | Section A - Floor 4 | 2 days | 2006-10-25 | 2006-10-26
96 | Section C - Floor 1 | 4 days | 2006-11-20 | 2006-11-23
97 | Section C - Floor 2 | 4 days | 2006-12-05 | 2006-12-08
98 | Section C - Floor 3 | 4 days | 2006-12-20 | 2006-12-25
99 | Section B - Floor 1 | 2 days | 2006-12-27 | 2006-12-28
100 | Crescent - Floor 1 | 2 days | 2007-01-02 | 2007-01-03
101 | Section C - Floor 4 | 4 days | 2007-01-09 | 2007-01-12
102 | Section B - Floor 2 | 2 days | 2007-01-16 | 2007-01-17
103 | Crescent - Floor 2 | 2 days | 2007-01-22 | 2007-01-23
104 | Section B - Floor 3 | 2 days | 2007-02-01 | 2007-02-02
105 | Crescent - Floor 3 | 2 days | 2007-02-07 | 2007-02-08
106 | Section B - Floor 4 | 2 days | 2007-02-21 | 2007-02-22
107 | Crescent - Floor 4 | 2 days | 2007-02-27 | 2007-02-28
108 | Drywall and Ceilings | 243 days | 2006-08-14 | 2007-07-18
109 | RI Metal Studs for Walls - Section A | 42 days | 2006-08-14 | 2006-10-10
110 | Rock/Tape/Finish Walls | 62 days | 2006-10-02 | 2006-12-26
111 | RI Metal Studs for Walls - Section C | 51 days | 2006-10-20 | 2006-12-29
112 | Install Rock/Hung Ceiling - Sections A & B | 71 days | 2006-10-23 | 2007-01-29
113 | RI Metal Studs for Walls - Section B | 49 days | 2006-11-24 | 2007-01-31
114 | RI Metal Studs for Walls - Crescent | 50 days | 2006-11-29 | 2007-02-06
115 | Rock/Tape/Finish Walls - Crescent | 67 days | 2007-01-04 | 2007-04-06
116 | Install Rock/Hung Ceiling - Crescent | 64 days | 2007-01-30 | 2007-04-27
117 | Rock/Tape/Finish Walls - Section C | 53 days | 2007-04-09 | 2007-06-20
118 | Install Rock/Hung Ceiling - Section C | 58 days | 2007-04-30 | 2007-07-18
119 | Painting Wall Covering | 186 days | 2006-11-14 | 2007-07-31
120 | Finish Painting - Sections A & B Floor 1 | 10 days | 2006-11-14 | 2006-11-27
121 | Finish Painting - Sections A & B Floor 2 | 10 days | 2006-12-06 | 2006-12-19
122 | Finish Painting - Sections A & B Floor 3 | 12 days | 2007-01-02 | 2007-01-17
123 | Finish Painting - Sections A & B Floor 4 | 11 days | 2007-01-30 | 2007-02-13
124 | Finish Paintings - Crescent Floor 1 | 11 days | 2007-02-26 | 2007-03-12
125 | Finish Paintings - Crescent Floor 2 | 11 days | 2007-03-20 | 2007-04-03
126 | Finish Paintings - Crescent Floor 3 | 10 days | 2007-04-10 | 2007-04-23
127 | Finish Paintings - Crescent Floor 4 | 10 days | 2007-04-30 | 2007-05-11
128 | Finish Painting - Section C Floor 1 | 10 days | 2007-05-18 | 2007-05-31
129 | Finish Painting - Section C Floor 2 | 9 days | 2007-06-08 | 2007-06-20
130 | Finish Painting - Section C Floor 3 | 10 days | 2007-06-28 | 2007-07-11
131 | Finish Painting - Section C Floor 4 | 9 days | 2007-07-19 | 2007-07-31
132 | Finish Carpentry | 194 days | 2006-11-28 | 2007-08-24
133 | Install Millwork - Sections A & B | 75 days | 2006-11-28 | 2007-03-12
134 | Install Millwork - Crescent | 63 days | 2007-03-13 | 2007-06-07
135 | Install Millwork - Section C | 61 days | 2007-06-01 | 2007-08-24
136 | Casework | 194 days | 2006-11-28 | 2007-08-24
137 | Install Casework - Sections A & B | 75 days | 2006-11-28 | 2007-03-12
138 | Install Casework - Crescent | 63 days | 2007-03-13 | 2007-06-07
139 | Install Casework - Section C | 61 days | 2007-06-01 | 2007-08-24
140 | Bathroom Tile | 248 days | 2006-09-06 | 2007-08-17
141 | Install Bathroom Ceramic Tile - Sections A & B | 130 days | 2006-09-06 | 2007-03-06
142 | Install Bathroom Ceramic Tile - Crescent | 59 days | 2007-01-30 | 2007-04-20
143 | Install Bathroom Ceramic Tile - Sections C | 82 days | 2007-04-26 | 2007-08-17
144 | Carpeting | 187 days | 2006-12-29 | 2007-09-17
145 | Install Floor Covering - Sections A & B | 88 days | 2006-12-29 | 2007-05-01
146 | Install Floor Covering - Crescent | 53 days | 2007-04-05 | 2007-06-18
147 | Install Floor Covering - Section C | 57 days | 2007-06-29 | 2007-09-17
148 | Terazzo | 233 days | 2006-12-29 | 2007-11-20
149 | Install Terazzo - Sections A & B | 70 days | 2006-12-29 | 2007-04-05
150 | Install Terazzo - Sections Crescent | 96 days | 2007-04-26 | 2007-09-06
151 | Install Terazzo - Sections C | 53 days | 2007-09-07 | 2007-11-20
152 | Mechanical and Plumbing | 102 days | 2006-07-10 | 2006-11-28
153 | RI Plumbing Chase & Risers - Section A | 7 days | 2006-07-10 | 2006-07-18
154 | RI HVAC Risers - Section A | 10 days | 2006-07-10 | 2006-07-21
155 | RI Plumbing Chase & Risers - Section B | 7 days | 2006-08-04 | 2006-08-14
156 | RI HVAC Risers - Section B | 10 days | 2006-08-04 | 2006-08-17
157 | RI HVAC in Ceilings - Section C | 57 days | 2006-08-07 | 2006-10-24
158 | RI Plumbing in Bathrooms - Section C | 41 days | 2006-08-07 | 2006-10-02
159 | RI HVAC on Roof - Section B | 21 days | 2006-08-11 | 2006-09-08
160 | RI Plumbing in Bathrooms - Section A | 42 days | 2006-08-14 | 2006-10-10
161 | RI HVAC in Ceilings - Section A | 42 days | 2006-08-14 | 2006-10-10
162 | RI Plumbing Chase & Risers - Section C | 13 days | 2006-08-16 | 2006-09-01
163 | RI HVAC Risers - Section C | 17 days | 2006-08-16 | 2006-09-07
164 | RI Plumbing Chase & Risers - Crescent | 7 days | 2006-08-24 | 2006-09-01
165 | RI HVAC Risers - Crescent | 11 days | 2006-08-24 | 2006-09-07
166 | RI HVAC in Ceilings - Section B | 26 days | 2006-08-28 | 2006-10-02
167 | RI Plumbing in Bathrooms - Section B | 42 days | 2006-08-28 | 2006-10-24
168 | RI Plumbing in Bathrooms - Crescent | 40 days | 2006-08-28 | 2006-10-20
169 | RI HVAC in Ceilings - Section Crescent | 20 days | 2006-09-05 | 2006-10-02
170 | RI HVAC on Roof - Crescent | 21 days | 2006-09-21 | 2006-10-19
171 | RI HVAC on Roof - Section A | 21 days | 2006-10-02 | 2006-10-30
172 | RI HVAC on Roof - Section C | 40 days | 2006-10-04 | 2006-11-28
173 | Test & Balance HVAC | 32 days | 2007-08-28 | 2007-10-10
174 | Comission Building HVAC System | 32 days | 2007-08-28 | 2007-10-10
175 | Test & Balance HVAC - Section C | 16 days | 2007-08-28 | 2007-09-18
176 | Test & Balance HVAC - Crescent | 10 days | 2007-09-12 | 2007-09-25
177 | Test & Balance HVAC - Section A | 10 days | 2007-09-19 | 2007-10-02
178 | Test & Balance HVAC - Section B | 11 days | 2007-09-26 | 2007-10-10
179 | Electrical | 379 days | 2006-04-28 | 2007-10-10
180 | Install Underslab Electrical - Section C | 10 days | 2006-04-28 | 2006-05-11
181 | RI Electrical Risers - Section A | 10 days | 2006-07-10 | 2006-07-21
182 | Install Underslab Electrical - Section A | 10 days | 2006-07-12 | 2006-07-25
183 | Install Underslab Electical - Section B | 10 days | 2006-07-26 | 2006-08-08
184 | RI Electrical Risers - Section B | 10 days | 2006-08-04 | 2006-08-17
185 | RI Elec. In Ceilings - Section C | 18 days | 2006-08-07 | 2006-08-30
186 | RI Elec. On Roof - Section B | 15 days | 2006-08-11 | 2006-08-31
187 | RI Elec. In Ceilings - Section A | 21 days | 2006-08-14 | 2006-09-11
188 | RI Electrical Risers - Section C | 10 days | 2006-08-16 | 2006-08-29
189 | Install Underslab Electrical - Crescent | 10 days | 2006-08-18 | 2006-08-31
190 | RI Electrical Risers - Crescent | 11 days | 2006-08-24 | 2006-09-07
191 | RI Electrical Risers - Section C | 11 days | 2006-08-24 | 2006-09-07
192 | RI Elec. In Ceilings - Section B | 21 days | 2006-08-28 | 2006-09-25
193 | RI Elec. In Ceilings - Section C | 21 days | 2006-08-28 | 2006-09-25
194 | RI Elec. In Walls - Section A | 42 days | 2006-08-28 | 2006-10-24
195 | RI Elec. In Ceilings - Crescent | 15 days | 2006-09-05 | 2006-09-25
196 | RI Elec. On Roof - Crescent | 16 days | 2006-09-21 | 2006-10-12
197 | RI Elec. On Roof - Section A | 16 days | 2006-10-02 | 2006-10-23
198 | Install Underslab Electrical - Section C | 11 days | 2006-10-03 | 2006-10-17
199 | RI Elec. On Roof - Section C | 15 days | 2006-10-04 | 2006-10-24
200 | RI Elec. On Roof - Section C | 16 days | 2006-10-30 | 2006-11-20
201 | RI Elec. In Walls - Section C | 40 days | 2006-11-07 | 2007-01-01
202 | RI Elec. In Walls - Section C | 40 days | 2006-11-14 | 2007-01-08
203 | RI Elec. In Walls - Section B | 40 days | 2006-12-11 | 2007-02-02
204 | RI Elec. In Walls - Crescent | 40 days | 2006-12-14 | 2007-02-07
205 | Comission Building Elec/Security/Data Sys. | 30 days | 2007-08-30 | 2007-10-10
206 | Elevators | 195 days | 2006-02-01 | 2006-10-31
207 | Install Elevator #4 Caisson | 2 days | 2006-02-01 | 2006-02-02
208 | Install Elevator #3 Caisson | 2 days | 2006-03-14 | 2006-03-15
209 | Install Elevator #1 Caisson | 2 days | 2006-04-14 | 2006-04-17
210 | Install Elevator #2 Caisson | 2 days | 2006-05-01 | 2006-05-02
211 | Install Elevator #1 | 30 days | 2006-08-25 | 2006-10-05
212 | Install Elevator #4 | 30 days | 2006-08-30 | 2006-10-10
213 | Install Elevator #2 | 30 days | 2006-09-19 | 2006-10-30
214 | Install Elevator #3 | 30 days | 2006-09-20 | 2006-10-31
215 | Final Hardscape & Paving | 63 days | 2007-04-16 | 2007-07-11
216 | Final Hardscap & Paving - Section C | 45 days | 2007-04-16 | 2007-06-15
217 | Final Hardscap & Paving - Section A | 45 days | 2007-04-17 | 2007-06-18
218 | Final Hardscap & Paving - Section B | 45 days | 2007-04-17 | 2007-06-18
219 | Final Hardscap & Paving - Crescent | 22 days | 2007-06-12 | 2007-07-11
220 | Final Landscaping | 71 days | 2007-05-16 | 2007-08-22
221 | Final Landscaping - SOB | 30 days | 2007-05-16 | 2007-06-26
222 | Final Landscaping - SOE | 30 days | 2007-07-12 | 2007-08-22
223 | Owner FFE | 45 days | 2007-09-27 | 2007-11-28
224 | Move In | 45 days | 2007-09-27 | 2007-11-28
225 | Substantial Completion | 0 days | 2007-11-28 | 2007-11-28
227 | Spring Semester Begins | 0 days | 2008-01-14 | 2008-01-14

## 출처
출처 URL | https://www.engr.psu.edu/ae/thesis/portfolios/2008/lef143/images/FINAL SCHEDULE.pdf
옮긴 날짜 | 2026-10-01
검증 | 행별 기간 = 시작~종료 월~금 근무일수(±1일, 반일 요약행 1건 제외) 일치